## extracted_excel_jira
clientName | clientUserName | clientToken | projectId | projectName | sprintId | sprintName | Summary | Issue key | Issue id | Parent id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Project url | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Labels | Description | Environment | Watchers | Watchers Id | Log Work | Log Work | Log Work | Log Work | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Security Level | Custom field (Actual end) | Custom field (Actual start) | Custom field (Ai Estimate) | Custom field (Atlas project key) | Custom field (Atlas project status) | Custom field (Change reason) | Custom field (Change risk) | Custom field (Change type) | Custom field (Compass) | Custom field (Development) | Custom field (Epic Color) | Custom field (Epic Name) | Custom field (Epic Status) | Custom field (Impact) | Custom field (Issue color) | Custom field (Locked forms) | Custom field (Open forms) | Custom field (Rank) | Custom field (Request Type) | Sprint | Custom field (Start date) | Custom field (Story Points) | Custom field (Story point estimate) | Custom field (Submitted forms) | Custom field (Target end) | Custom field (Target start) | Custom field (Team) | Custom field (Total forms) | Custom field ([CHART] Date of First Response) | Parent | Parent summary | Status Category
clavrit | mallika@clavrit.com | ATATT3xFfGF0yCReGfI8FZj71eGSaisgf1sFLwmnWUKfJwOKGC13l9mJXDw7yOQEmo5bXYC9aEQSAD3lVmjrJrqrjZBxFGAPUmgepaXfKF8AXt3o14dkY7uXmtW6c-sK0G2-rXuXyOW2SDz5nckRz0PLzHezGh1isPlhsonGDVh8QtUh77kbtRQ=5894E0AC | 4 | Estimation-Tool | 18 | ET Sprint 3 | Tune the model training parameters to improve accuracy - 5th variation | ET-128 | 10261 | 10135 | Sub-task | To Do | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium |  | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | 2023-11-01 22:09 | 2023-11-07 07:57 | 2023-11-23 10:45 |  |  | 0 | EST_AI | Experiment with model hyperparameters by observing the loss and accuracy graphs. |  | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 |  |  |  |  | 43200 | 43200 |  | 0% | 43200 | 43200 | [11 empty] | {} | [7 empty] | 0¦i001iv: |  | ET Sprint 3 | [9 empty] | 10135 | Improve Model Performance (Iterative Process; 1 iteration = 7 Days) | To Do
[7 empty] | Tune the model training parameters to improve accuracy - 4th variation | ET-127 | 10260 | 10135 | Sub-task | To Do | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium |  | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | 2023-11-01 22:07 | 2023-11-22 15:29 | 2023-11-23 10:45 |  |  | 0 | EST_AI | Experiment with model hyperparameters by observing the loss and accuracy graphs. |  | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 |  |  |  |  | 43200 | 43200 |  | 0% | 43200 | 43200 |  |  |  |  | 7 | [6 empty] | {} | [7 empty] | 0¦i001in: |  | ET Sprint 3 | [9 empty] | 10135 | Improve Model Performance (Iterative Process; 1 iteration = 7 Days) | To Do
[7 empty] | Tune the model training parameters to improve accuracy - 3rd variation | ET-126 | 10259 | 10135 | Sub-task | To Do | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium |  | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | 2023-11-01 22:07 | 2023-11-22 15:29 | 2023-11-23 10:46 |  |  | 0 | EST_AI | Experiment with model hyperparameters by observing the loss and accuracy graphs. |  | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 |  |  |  |  | 43200 | 43200 |  | 0% | 43200 | 43200 |  |  |  |  | 8 | [6 empty] | {} | [7 empty] | 0¦i001if: |  | ET Sprint 3 | [9 empty] | 10135 | Improve Model Performance (Iterative Process; 1 iteration = 7 Days) | To Do
[7 empty] | Tune the model training parameters to improve accuracy - 2nd variation | ET-125 | 10258 | 10135 | Sub-task | To Do | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium |  | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | 2023-11-01 22:07 | 2023-11-07 07:56 | 2023-11-23 10:46 |  |  | 0 | EST_AI | Experiment with model hyperparameters by observing the loss and accuracy graphs. |  | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 |  |  |  |  | 43200 | 43200 |  | 0% | 43200 | 43200 | [11 empty] | {} | [7 empty] | 0¦i001i7: |  | ET Sprint 3 | [9 empty] | 10135 | Improve Model Performance (Iterative Process; 1 iteration = 7 Days) | To Do
[7 empty] | Tune the model training parameters to improve accuracy - 1st variation | ET-124 | 10257 | 10135 | Sub-task | To Do | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium |  | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | 2023-11-01 22:06 | 2023-11-22 15:29 | 2023-11-23 10:46 |  |  | 0 | EST_AI | Experiment with model hyperparameters by observing the loss and accuracy graphs. |  | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 |  |  |  |  | 43200 | 43200 |  | 0% | 43200 | 43200 |  |  |  |  | 0 | [6 empty] | {} | [7 empty] | 0¦i001hz: |  | ET Sprint 3 | [9 empty] | 10135 | Improve Model Performance (Iterative Process; 1 iteration = 7 Days) | To Do
[7 empty] | Evaluate the model | ET-123 | 10256 | 10133 | Sub-task | To Do | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium |  | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | 2023-11-01 22:01 | 2023-11-07 07:54 | 2023-11-23 10:46 |  |  | 0 | EST_AI | Evaluate the trained model performance on the validation dataset and compare its performance by metrics, loss, and accuracy graphs. |  | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 |  |  |  |  | 28800 | 28800 |  | 0% | 28800 | 28800 | [11 empty] | {} | [7 empty] | 0¦i000kz:hi |  | ET Sprint 3 | [9 empty] | 10133 | Train and evaluate the model on added features | To Do
[7 empty] | Train the model | ET-122 | 10255 | 10133 | Sub-task | In Progress | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium |  | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | 2023-11-01 22:01 | 2023-11-22 15:23 | 2023-11-23 10:46 |  |  | 0 | EST_AI | Use a high computational system for training the model. Execute the model training script and monitor the performance of the model. |  | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | ;20/Nov/23 3:03 PM;712020:46506adc-510d-430a-bf3b-8f59643806df;28800 | ;21/Nov/23 2:58 PM;712020:46506adc-510d-430a-bf3b-8f59643806df;28800 | ;22/Nov/23 3:03 PM;712020:46506adc-510d-430a-bf3b-8f59643806df;14400 |  | 86400 | 14400 | 72000 | 83% | 86400 | 14400 | 72000 |  |  |  | 1 | [6 empty] | {} | [7 empty] | 0¦i000kz:h |  | ET Sprint 3 | [9 empty] | 10133 | Train and evaluate the model on added features | In Progress
[7 empty] | Create training and utility scripts | ET-121 | 10254 | 10133 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | 2023-11-01 21:58 | 2023-11-15 14:11 | 2023-11-23 10:46 | 2023-11-15 14:11 |  | 0 | EST_AI | Training script - Create a model training script containing all the required hyperparameters and set the fit function for the model. Utility scripts - Create a helper script. |  | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | ;08/Nov/23 3:05 PM;712020:46506adc-510d-430a-bf3b-8f59643806df;21600 | ;15/Nov/23 2:11 PM;712020:46506adc-510d-430a-bf3b-8f59643806df;7200 |  |  | 28800 | 0 | 28800 | 100% | 28800 | 0 | 28800 | [10 empty] | {} | [7 empty] | 0¦i000kz:g |  | ET Sprint 3 | [9 empty] | 10133 | Train and evaluate the model on added features | Done
[7 empty] | Create model architecture, Define loss function, optimizer, metrics, training and validation parameters | ET-120 | 10253 | 10133 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | 2023-11-01 21:57 | 2023-11-07 07:49 | 2023-11-23 10:46 | 2023-11-06 15:01 |  | 0 | EST_AI | Model architecture - Define the model branches, layers, activation functions, and kernel initializers. Loss function - Speficy the loss for the model. Optimizer - Specify the optimizer to minimize the loss function. Metrics - Speficy the accuracy. Training & Validation parameters - Speficy other hyperparameters |  | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | ;03/Nov/23 3:05 PM;712020:46506adc-510d-430a-bf3b-8f59643806df;28800 |  |  |  | 28800 | 0 | 28800 | 100% | 28800 | 0 | 28800 | [10 empty] | {} | [7 empty] | 0¦i000kz:f |  | ET Sprint 3 | [9 empty] | 10133 | Train and evaluate the model on added features | Done
[7 empty] | Create data preprocessing, feature engineering and feature encoding modules | ET-119 | 10252 | 10133 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | 2023-11-01 21:53 | 2023-11-07 07:46 | 2023-11-23 10:46 | 2023-11-06 15:05 |  | 0 | EST_AI | Data preprocessing - Data cleaning and transforming script, Feature engineering - Python script to create and select features from raw data, Feature encoding - Converts categorical or text values into numerical vectors |  | Abhash Srivastava | 70121:621de347-3986-446f-8c5f-e2b52b8f8924 | ;06/Nov/23 3:04 PM;712020:46506adc-510d-430a-bf3b-8f59643806df;7200 | ;06/Nov/23 3:05 PM;712020:46506adc-510d-430a-bf3b-8f59643806df;21600 |  |  | 28800 | 0 | 28800 | 100% | 28800 | 0 | 28800 | [10 empty] | {} | [7 empty] | 0¦i000kz:d |  | ET Sprint 3 | [9 empty] | 10133 | Train and evaluate the model on added features | Done
[7 empty] | BE-JIRA integration with authentication and authorizations | ET-118 | 10251 | 10112 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | mallika gopal | 712020:a00b078e-fffc-4e59-91a6-69dbdedebd00 | mallika gopal | 712020:a00b078e-fffc-4e59-91a6-69dbdedebd00 | mallika gopal | 712020:a00b078e-fffc-4e59-91a6-69dbdedebd00 | 2023-11-01 17:57 | 2023-11-22 16:14 | 2023-11-23 10:44 | 2023-11-14 08:12 |  | 0 |  | Implementating authentication and authorizations of Jira rest service. |  | mallika gopal | 712020:a00b078e-fffc-4e59-91a6-69dbdedebd00 |  |  |  |  | 28800 | 28800 |  | 0% | 28800 | 28800 |  |  |  |  | 7 | [6 empty] | {} | [7 empty] | 0¦i001gn: |  | ET Sprint 3 | [9 empty] | 10112 | JIRA integration with authentication and authorizations (Assuming we have the Jira account and credentials) | Done
[7 empty] | BE - Status of task already fetched from JIRA and updated to Jira | ET-117 | 10250 | 10100 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | mallika gopal | 712020:a00b078e-fffc-4e59-91a6-69dbdedebd00 | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-11-01 16:02 | 2023-11-22 14:19 | 2023-11-22 14:20 | 2023-11-16 08:06 |  | 0 | EST_BE | Implementing sync and update feature for modified tasks. |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;09/Nov/23 8:10 AM;712020:a00b078e-fffc-4e59-91a6-69dbdedebd00;28800 |  |  |  | 57600 | 28800 | 28800 | 50% | 57600 | 28800 | 28800 |  |  |  | 2 | [6 empty] | {} | [7 empty] | 0¦i001gf: |  | ET Sprint 3 | [9 empty] | 10100 | Status of task already fetched from JIRA and updated to Jira | Done
[7 empty] | FE - Status of task already fetched from JIRA and updated to Jira | ET-116 | 10249 | 10100 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-11-01 16:02 | 2023-11-15 13:48 | 2023-11-22 11:06 | 2023-11-15 13:47 |  | 0 | EST_FE | Implemention of sync and update feature for modified tasks. |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;15/Nov/23 1:47 PM;624e81a645ece00069ce5a1d;28800 |  |  |  | 28800 | 0 | 28800 | 100% | 28800 | 0 | 28800 | [10 empty] | {} | [7 empty] | 0¦i001g7: |  | ET Sprint 3 | [9 empty] | 10100 | Status of task already fetched from JIRA and updated to Jira | Done
[7 empty] | BE - Update AI estimates to JIRA Single/Bulk | ET-115 | 10248 | 10101 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | mallika gopal | 712020:a00b078e-fffc-4e59-91a6-69dbdedebd00 | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-11-01 16:02 | 2023-11-20 10:38 | 2023-11-22 11:06 | 2023-11-17 14:31 |  | 0 | EST_BE | getting AI estimates and updating to JIRA. |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;17/Nov/23 2:20 PM;712020:a00b078e-fffc-4e59-91a6-69dbdedebd00;28800 | ;20/Nov/23 10:37 AM;712020:a00b078e-fffc-4e59-91a6-69dbdedebd00;28800 |  |  | 57600 | 0 | 57600 | 100% | 57600 | 0 | 57600 | [10 empty] | {} | [7 empty] | 0¦i001fz: |  | ET Sprint 3 | [9 empty] | 10101 | Update AI estimates to JIRA Single/Bulk | Done
[7 empty] | FE - Update AI estimates to JIRA Single/Bulk | ET-114 | 10247 | 10101 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Manish Chandra | 712020:c8576f14-b124-475b-9507-ea48efeaeaef | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-11-01 16:01 | 2023-11-22 17:50 | 2023-11-22 11:06 | 2023-11-22 17:50 |  | 0 | EST_FE |  |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;20/Nov/23 2:10 PM;624e81a645ece00069ce5a1d;28800 | ;22/Nov/23 5:50 PM;624e81a645ece00069ce5a1d;28800 |  |  | 57600 | 0 | 57600 | 100% | 57600 | 0 | 57600 | [10 empty] | {} | [7 empty] | 0¦i001fr: |  | ET Sprint 3 | [9 empty] | 10101 | Update AI estimates to JIRA Single/Bulk | Done
[7 empty] | BE - Task details page/popup - with edit features | ET-113 | 10246 | 10102 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | mallika gopal | 712020:a00b078e-fffc-4e59-91a6-69dbdedebd00 | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-11-01 16:01 | 2023-11-22 16:13 | 2023-11-22 16:13 | 2023-11-17 15:00 |  | 0 | EST_BE | Implementation of each task details saving into DB and Jira after modifications. |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;16/Nov/23 8:12 AM;712020:a00b078e-fffc-4e59-91a6-69dbdedebd00;28800 | ;20/Nov/23 10:01 AM;712020:a00b078e-fffc-4e59-91a6-69dbdedebd00;28800 |  |  | 57600 | 0 | 57600 | 100% | 57600 | 0 | 57600 |  |  |  | 8 | [6 empty] | {} | [7 empty] | 0¦i001fj: |  | ET Sprint 3 | [9 empty] | 10102 | Task details page/popup - with edit features | Done
[7 empty] | FE - Task details page/popup - with edit features | ET-112 | 10245 | 10102 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-11-01 16:01 | 2023-11-22 15:23 | 2023-11-22 11:05 | 2023-11-08 14:27 |  | 0 | EST_FE | Implementation of a popup for each task from task details page. |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;06/Nov/23 6:07 PM;624e81a645ece00069ce5a1d;28800 | ;07/Nov/23 5:46 PM;624e81a645ece00069ce5a1d;28800 |  |  | 57600 | 0 | 57600 | 100% | 57600 | 0 | 57600 | [10 empty] | {} | [7 empty] | 0¦i001fb: |  | ET Sprint 3 | [9 empty] | 10102 | Task details page/popup - with edit features | Done
[7 empty] | FE - Sorting and filter on datatables | ET-111 | 10244 | 10094 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-11-01 16:00 | 2023-11-22 11:12 | 2023-11-07 17:39 | 2023-11-06 14:19 |  | 0 | EST_FE | implementation of Sorting and filtering functionality for data tables. |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;06/Nov/23 2:18 PM;624e81a645ece00069ce5a1d;28800 |  |  |  | 28800 | 0 | 28800 | 100% | 28800 | 0 | 28800 |  |  |  | 8 | [6 empty] | {} | [7 empty] | 0¦i000l1:t |  | ET Sprint 3 | [9 empty] | 10094 | Sorting and filter on datatables | Done
[7 empty] | BE - List of tasks - Edit Page Sync /update feature | ET-101 | 10180 | 10099 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | mallika gopal | 712020:a00b078e-fffc-4e59-91a6-69dbdedebd00 | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-10-17 14:37 | 2023-11-22 16:02 | 2023-11-20 09:40 | 2023-11-08 13:17 |  | 0 | EST_BE | Implementing Sync feature after doing changes in list of tasks. |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;20/Nov/23 9:41 AM;712020:a00b078e-fffc-4e59-91a6-69dbdedebd00;28800 |  |  |  | 28800 | 0 | 28800 | 100% | 28800 | 0 | 28800 |  |  |  | 0 | [6 empty] | {} | [7 empty] | 0¦i000i3:v |  | ET Sprint 3 | [9 empty] | 10099 | List of tasks - Edit Page Sync /update feature | Done
[7 empty] | FE - List of tasks - Edit Page Sync /update feature | ET-100 | 10179 | 10099 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-10-17 14:37 | 2023-11-23 09:04 | 2023-11-23 09:02 | 2023-11-17 12:33 |  | 0 | EST_FE |  |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;17/Nov/23 12:32 PM;624e81a645ece00069ce5a1d;28800 |  |  |  | 28800 | 0 | 28800 | 100% | 28800 | 0 | 28800 |  |  |  | 0 | [6 empty] | {} | [7 empty] | 0¦i000i3:r |  | ET Sprint 3 | [9 empty] | 10099 | List of tasks - Edit Page Sync /update feature | Done
[7 empty] | BE - List of tasks - Edit Page | ET-99 | 10178 | 10098 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | mallika gopal | 712020:a00b078e-fffc-4e59-91a6-69dbdedebd00 | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-10-17 14:36 | 2023-11-23 09:00 | 2023-11-23 09:00 | 2023-11-08 13:17 |  | 0 | EST_BE | getting list of task details from JIRA, DB and AI estimation . |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;02/Nov/23 5:43 PM;712020:a00b078e-fffc-4e59-91a6-69dbdedebd00;28800 |  |  |  | 28800 | 0 | 28800 | 100% | 28800 | 0 | 28800 |  |  |  | 4 | [6 empty] | {} | [7 empty] | 0¦i000i4:r |  | ET Sprint 3 | [9 empty] | 10098 | List of tasks - Edit Page | Done
[7 empty] | FE - List of tasks - Edit Page | ET-98 | 10177 | 10098 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-10-17 14:36 | 2023-11-08 14:38 | 2023-11-02 09:50 | 2023-11-06 14:18 |  | 0 | EST_FE | Implementation of listing all tasks on a single page. |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;03/Nov/23 1:59 PM;624e81a645ece00069ce5a1d;28800 |  |  |  | 28800 | 0 | 28800 | 100% | 28800 | 0 | 28800 | [10 empty] | {} | [7 empty] | 0¦i000i4:i |  | ET Sprint 3 | [9 empty] | 10098 | List of tasks - Edit Page | Done
[7 empty] | BE - List of tasks - list view along edit and sync feature | ET-97 | 10176 | 10097 | Sub-task | In Progress | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium |  | mallika gopal | 712020:a00b078e-fffc-4e59-91a6-69dbdedebd00 | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-10-17 14:36 | 2023-11-22 13:11 | 2023-11-22 12:13 |  |  | 0 | EST_BE | Implementation of edit and task feature on list of tasks. |  | Parveen raaj | 624e81a645ece00069ce5a1d |  |  |  |  | 57600 | 57600 |  | 0% | 57600 | 57600 |  |  |  |  | 2 | [6 empty] | {} | [7 empty] | 0¦i000i6: |  | ET Sprint 3 | [9 empty] | 10097 | List of tasks - list view along edit and sync feature | In Progress
[7 empty] | FE - List of tasks - list view along edit and sync feature | ET-96 | 10175 | 10097 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | Parveen raaj | 624e81a645ece00069ce5a1d | 2023-10-17 14:35 | 2023-11-22 12:31 | 2023-11-23 10:46 | 2023-11-20 14:10 |  | 0 | EST_FE | Implementation of edit and task feature on list of tasks. |  | Parveen raaj | 624e81a645ece00069ce5a1d | ;14/Nov/23 8:04 AM;624e81a645ece00069ce5a1d;28800 | ;20/Nov/23 2:10 PM;624e81a645ece00069ce5a1d;28800 |  |  | 57600 | 0 | 57600 | 100% | 57600 | 0 | 57600 |  |  |  | 6 | [6 empty] | {} | [7 empty] | 0¦i000i5: |  | ET Sprint 3 | [9 empty] | 10097 | List of tasks - list view along edit and sync feature | Done
[7 empty] | Task 2: Changes in model architecture to add new features | ET-83 | 10162 | 10131 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-11 15:24 | 2023-11-07 07:55 | 2023-11-23 10:46 | 2023-11-06 15:02 |  | 0 | EST_AI | Add branches and layers in model architecture to use new input features. |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | ;06/Nov/23 3:02 PM;712020:46506adc-510d-430a-bf3b-8f59643806df;7200 |  |  |  | 7200 | 0 | 7200 | 100% | 7200 | 0 | 7200 | [10 empty] | {} | [7 empty] | 0¦i000l2:i |  | ET Sprint 3 | [9 empty] | 10131 | Changes in model architecture to add new features | Done
[7 empty] | Task 1 : Changes in model architecture to add new features | ET-82 | 10161 | 10131 | Sub-task | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-11 15:23 | 2023-11-07 07:55 | 2023-11-23 10:46 | 2023-10-17 15:28 |  | 0 | EST_AI | Add branches and layers in model architecture to use new input features. |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | ;17/Oct/23 4:22 PM;70121:621de347-3986-446f-8c5f-e2b52b8f8924;7200 |  |  |  | 7200 | 0 | 7200 | 100% | 7200 | 0 | 7200 | [10 empty] | {} | [7 empty] | 0¦i000l2: |  | ET Sprint 3 | [9 empty] | 10131 | Changes in model architecture to add new features | Done
[7 empty] | Set up environment and install packages | ET-69 | 10148 |  | Story | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Rushikesh Mahendra Raut | 712020:29543410-da57-4a0a-bde6-bbfdc84a0203 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 15:33 | 2023-11-07 07:59 | 2023-11-23 10:46 | 2023-11-06 12:38 |  | 0 | EST_INFRA | Setting up Python environment in AWS EC-2 Instance and installing required libraries and packages. |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | Created python environment on server and installed all the requied packages .;06/Nov/23 12:38 PM;712020:29543410-da57-4a0a-bde6-bbfdc84a0203;14400 |  |  |  | 14400 | 0 | 14400 | 100% | 14400 | 0 | 14400 | [10 empty] | {} | [7 empty] | 0¦i000l1:9 |  | ET Sprint 3 |  | 0.5 | [9 empty] | Done
[7 empty] | Set up JDK and integrate with backend | ET-67 | 10146 |  | Story | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Rushikesh Mahendra Raut | 712020:29543410-da57-4a0a-bde6-bbfdc84a0203 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 15:33 | 2023-11-07 07:58 | 2023-11-01 13:34 | 2023-11-03 10:38 |  | 0 | EST_BE | Setup the Java Development Kit in the project environment and integrate it with the Django. |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | ;31/Oct/23 8:28 AM;712020:29543410-da57-4a0a-bde6-bbfdc84a0203;14400 | After discussion with team , Finalized the input parameters and input type to be provided to POST request.;01/Nov/23 10:36 AM;712020:29543410-da57-4a0a-bde6-bbfdc84a0203;14400 | Updated the input fields in Django project.;01/Nov/23 4:57 PM;712020:29543410-da57-4a0a-bde6-bbfdc84a0203;14400 | ;03/Nov/23 10:38 AM;712020:29543410-da57-4a0a-bde6-bbfdc84a0203;14400 | 57600 | 0 | 57600 | 100% | 57600 | 0 | 57600 | [10 empty] | {} | [7 empty] | 0¦i000l1:4 |  | ET Sprint 3 |  | 2 | [9 empty] | Done
[7 empty] | Improve Model Performance (Iterative Process; 1 iteration = 7 Days) | ET-56 | 10135 |  | Story | To Do | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | High |  | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 15:30 | 2023-11-01 18:36 | 2023-11-20 09:43 |  |  | 0 | EST_AI |  |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 |  |  |  |  | 201600 | 201600 |  | 0% | 417600 | 417600 | [11 empty] | {} | [7 empty] | 0¦i000kz:i |  | ET Sprint 3 |  | 7 | [9 empty] | To Do
[7 empty] | Train and evaluate the model on added features | ET-54 | 10133 |  | Story | In Progress | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Highest |  | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 15:29 | 2023-11-07 07:59 | 2023-11-20 10:41 |  |  | 0 |  |  |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 |  |  |  |  | 201600 | 201600 |  | 0% | 403200 | 244800 | 158400 | [10 empty] | {} | [7 empty] | 0¦i000kz:9 |  | ET Sprint 3 |  | 7 | [9 empty] | In Progress
[7 empty] | Changes in model architecture to add new features | ET-52 | 10131 |  | Story | In Progress | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium |  | Aman Shrivastava | 712020:46506adc-510d-430a-bf3b-8f59643806df | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 15:27 | 2023-11-01 18:23 | 2023-11-23 10:46 |  |  | 0 | EST_AI |  |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | ;11/Oct/23 1:16 PM;712020:46506adc-510d-430a-bf3b-8f59643806df;14400 |  |  |  |  | 0 | 14400 |  | 14400 | 0 | 28800 | [10 empty] | {} | [7 empty] | 0¦i000l1: |  | ET Sprint 3 |  | 0.5 | [9 empty] | In Progress
[7 empty] | JIRA integration with authentication and authorizations (Assuming we have the Jira account and credentials) | ET-33 | 10112 |  | Story | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | mallika gopal | 712020:a00b078e-fffc-4e59-91a6-69dbdedebd00 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 15:01 | 2023-11-14 08:13 | 2023-11-20 10:41 | 2023-11-14 08:13 |  | 0 |  | Implementation of authentication and authorizations of Jira rest service. |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 |  |  |  |  | 28800 | 28800 |  | 0% | 57600 | 57600 | [11 empty] | {} | [7 empty] | 0¦i000kz: |  | ET Sprint 3 | [11 empty] | Done
[7 empty] | Validation - error and success messages for all pages | ET-28 | 10107 |  | Story | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Parveen raaj | 624e81a645ece00069ce5a1d | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 14:58 | 2023-11-14 16:35 | 2023-11-23 09:02 | 2023-11-14 16:35 |  | 0 | EST_FE | implementing error and success messages for all functionalities. |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | ;14/Nov/23 8:02 AM;624e81a645ece00069ce5a1d;28800 | ;14/Nov/23 4:35 PM;624e81a645ece00069ce5a1d;28800 |  |  | 57600 | 0 | 57600 | 100% | 57600 | 0 | 57600 | [10 empty] | {} | [7 empty] | 0¦i000kv: |  | ET Sprint 3 |  | 2 | [9 empty] | Done
[7 empty] | Task details page/popup - with edit features | ET-23 | 10102 |  | Story | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | clavrit-miror | 612b9aa0ae44ae0070903d22 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 14:56 | 2023-11-22 11:03 | 2023-11-23 07:49 | 2023-11-20 10:41 |  | 0 |  |  |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | [8 empty] | 115200 | 0 | 115200 |  |  |  | 4 | [6 empty] | {} | [7 empty] | 0¦i000i3:2 |  | ET Sprint 3 |  | 4 | [9 empty] | Done
[7 empty] | Update AI estimates to JIRA Single/Bulk | ET-22 | 10101 |  | Story | In Progress | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium |  | clavrit-miror | 612b9aa0ae44ae0070903d22 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 14:56 | 2023-11-10 14:59 | 2023-11-22 15:40 |  |  | 0 |  |  |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | [8 empty] | 115200 | 0 | 115200 | [10 empty] | {} | [7 empty] | 0¦i000i3:4 |  | ET Sprint 3 |  | 4 | [9 empty] | In Progress
[7 empty] | Status of task already fetched from JIRA and updated to Jira | ET-21 | 10100 |  | Story | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | clavrit-miror | 612b9aa0ae44ae0070903d22 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 14:56 | 2023-11-16 08:06 | 2023-11-22 11:13 | 2023-11-16 08:06 |  | 0 |  | Implemention of sync and update feature for modified tasks. |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | [8 empty] | 86400 | 28800 | 57600 | [10 empty] | {} | [7 empty] | 0¦i000i3:9 |  | ET Sprint 3 |  | 3 | [9 empty] | Done
[7 empty] | List of tasks - Edit Page Sync /update feature | ET-20 | 10099 |  | Story | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | clavrit-miror | 612b9aa0ae44ae0070903d22 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 14:55 | 2023-11-20 10:42 | 2023-11-23 09:06 | 2023-11-20 10:42 |  | 0 |  | implementing sync and update feature on task list. |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | [8 empty] | 57600 | 0 | 57600 | [10 empty] | {} | [7 empty] | 0¦i000i3:i |  | ET Sprint 3 |  | 2 | [9 empty] | Done
[7 empty] | List of tasks - Edit Page | ET-19 | 10098 |  | Story | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | clavrit-miror | 612b9aa0ae44ae0070903d22 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 14:55 | 2023-11-08 13:17 | 2023-11-23 09:00 | 2023-11-08 13:17 |  | 0 |  | Getting list of tasks from Jira based on sprintId |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | [8 empty] | 57600 | 0 | 57600 | [10 empty] | {} | [7 empty] | 0¦i000i4: |  | ET Sprint 3 |  | 2 | [9 empty] | Done
[7 empty] | List of tasks - list view along edit and sync feature | ET-18 | 10097 |  | Story | In Progress | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium |  | clavrit-miror | 612b9aa0ae44ae0070903d22 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 14:54 | 2023-11-22 10:50 | 2023-11-22 14:18 |  |  | 0 |  | Implementation of edit and task feature on list of tasks. |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | [8 empty] | 115200 | 57600 | 57600 |  |  |  | 4 | [6 empty] | {} | [7 empty] | 0¦i000i3: |  | ET Sprint 3 |  | 4 | [9 empty] | In Progress
[7 empty] | Sorting and filter on datatables | ET-15 | 10094 |  | Story | Done | ET | Estimation-Tool | software | clavrit-miror | 612b9aa0ae44ae0070903d22 |  |  | Medium | Done | Parveen raaj | 624e81a645ece00069ce5a1d | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | 2023-10-05 14:53 | 2023-11-22 11:11 | 2023-11-07 17:37 | 2023-11-16 08:28 |  | 0 | EST_FE |  |  | meenakshi chhaunker | 712020:640134b0-321f-4cd0-89a2-64cefd04b6b8 | [8 empty] | 28800 | 0 | 28800 |  |  |  | 12 | [6 empty] | {} | [7 empty] | 0¦i000l1:m |  | ET Sprint 3 |  | 1 | [9 empty] | Done